## 某项目
某项目开发计划跟踪表
业务模块 | 功能模块 | 程序 | 类型 | 功能点 | 状态 | 优先级 | 预计开发工时（人天） | 预计开发开始时间 | 预计开发完成时间 | 实际完成时间 | 责任人 | 协助人员 | 备注 | 进度 | 变更记录
流程图 | 堂食扫台码流程图 | [5 empty] | 1 | 2018.8.13 | 2018.8.13 | 2018.8.13 | flora |  |  | 100%%
flora
flora
51易餐网页面调整 | 首页 index.jsp | [6 empty] | 2018.8.2 | 2018.8.20 | 2018.8.3 | flora
| 餐厅查找 index_search.jsp | [8 empty] | 2018.8.3 | flora
| 餐厅预定 index_schedule_restaurant_list.jsp | [8 empty] | 2018.8.4 | flora
| 预定餐厅详情 restaurant_detail_info.jsp | [8 empty] | 2018.8.4 | flora
| 预定信息 index_schedule_info.jsp | [8 empty] | 2018.8.4 | flora
| 选择就餐日期 index_schedule_info.jsp | [8 empty] | 2018.8.8 | flora
| 生成订单 schedule_order_make.jsp | [8 empty] | 2018.8.16 | flora
| 常吃的菜 schedule_order_used.jsp | [8 empty] | 2018.8.16 | flora
| 餐厅晒单 schedule_order_menu.jsp | [8 empty] | 2018.8.16 | flora
| 邀请好友 schedule_order_invite_friend.jsp | [8 empty] | 2018.8.15 | flora
| 预定点单 schedule_order_panel.jsp | [8 empty] | 2018.8.5 | flora
| 预定点单页面 sechdule_order.jsp | [8 empty] | 2018.8.17
| 预定分享定位 index_schedule_order_share_edit.jsp | [8 empty] | 2018.8.17 | flora
| 预定结束点单并付款 schedule_order_detail.jsp | [8 empty] | 2018.8.5 | flora
| 付款 index_order_pay.jsp | [8 empty] | 2018.8.17 | flora
| 预定付款详情 index_order_pay_detail.jsp | [8 empty] | 2018.8.17 | flora
| 预定订单详情 index_schedule_order_detail.jsp | [8 empty] | 2018.8.15 | flora
| 预定信息分享设置 index_schedule_order_share_edit.jsp | [8 empty] | 2018.8.15 | flora
| 店内堂食 index_dine_in_restaurant_list.jsp | [8 empty] | 2018.8.17 | flora
| 食堂信息 index_dine_in_info.jsp | [8 empty] | 2018.8.17 | flora
| 邀请好友 dine_in_order_invite_friend.jsp | [8 empty] | 2018.8.17 | flora
| 食堂点单 dine_in_order_panel.jsp | [9 empty] | flora
| 食堂点单页面 dine_in_order.jsp | [8 empty] | 2018.8.17
| 生成订单 dine_in_order_make.jsp | [8 empty] | 2018.8.17 | flora
| 食堂订单详情 index_dine_in_order_detail.jsp | [9 empty] | flora
| 使用帮助 help_process.jsp | [9 empty] | flora
| 招聘 index_recruit_list.jsp | [9 empty] | flora
| 招聘详情 recruit_detail_info.jsp | [9 empty] | flora
| 会员注册 regitst.jsp | [9 empty] | flora
| 绑定授权 cellphone_bind.jsp | [9 empty] | flora
| 登陆 login.jsp | [8 empty] | 2018.8.6 | flora
| 忘记密码 forget_pwd.jsp | [8 empty] | 2018.8.6 | flora
| 定位 city_change.jsp | [9 empty] | flora
| 会员中心 index_member.jsp | [8 empty] | 2018.8.8 | flora
| 个人信息修改 member_info.jsp | [9 empty] | flora
| 好友管理 member_frends.jsp | [9 empty] | flora
| 好友申请 member_friends_apply.jsp | [9 empty] | flora
| 站内信 member_notice.jsp | [9 empty] | flora
| 我的预定订单 index_order_item.jsp | [9 empty] | flora
| 参与好友预定 index_order_item.jsp | [9 empty] | flora
| 堂食订单 index_order_item_dine_in.jsp | [9 empty] | flora
| 参与好友堂食 index_order_item_dine_in.jsp | [9 empty] | flora
| 关注的餐厅 index_attention.jsp | [9 empty] | flora
| 评论晒单 member_evaluate.jsp | [9 empty] | flora
| 订单投诉 member_order_complaints.jsp | [9 empty] | flora
| 支付记录 member_pay_history.jsp | [9 empty] | flora
| 修改登录密码 member_modify_pwd.jsp | [9 empty] | flora
| 手机绑定 member_phone_bundling.jsp | [9 empty] | flora
| 留言建议 member_advice.jsp | [9 empty] | flora
| 客服热线 | [9 empty] | flora
| 商务合作 member_join.jsp | [9 empty] | flora
Note on F2: 作者: 未开始,方案定义中,方案已确定,开发中,初步测试完成,集成测试完成,用户已确认